## Burndown Chart Template
Burndown Chart Template
Velocity = Total Story Points Delivered over a Sprint
The example below illustrates a basic example of a 4 Sprint Project. Being the Sprints in this case 2 weeks long this is a 2 month project.
It has 15 user stories in total. I've used the name "User Story #" in the essence of time, but you would of course write the actual user story using the format described in the other tab
Assumption: The team discards the user stories which aren't delivered
Sprint 1 |  | Story Points
User Story 6 |  | 3 |  | Note: this user story wasn't delivered in Sprint 1 since the team didn't have time to complete it
User Story 11 |  | 3
User Story 2 |  | 5
User Story 8 |  | 1
| Total | 12 | Velocity Sprint 1 | 9
Sprint 2
User Story 1 |  | 5
User Story 13 |  | 1
User Story 5 |  | 1
| Total | 7 | Velocity Sprint 2 | 7
Sprint 3
User Story 3 |  | 5
User Story 4 |  | 3
User Story 15 |  | 1
| Total | 9 | Velocity Sprint 3 | 9
Sprint 4
User Story 9 |  | 3 |  | Note: this user story wasn't delivered in Sprint 4 since the team didn't have time to complete it
User Story 7 |  | 5
User Story 14 |  | 3
User Story 10 |  | 1
User Story 12 |  | 1
| Total | 13 | Velocity Sprint 4 | 10
Total Story Points |  | 41 | Average Velocity | 8.75 | Which means that on average the team is delivering 9 story points per Sprint. This is known as the project's Velocity
This is an indication of execution that allows for future planning and workload management.
Traditional
Burndown Chart
Sprint | Remaining Story Points
1 | 41
2 | 32
3 | 25
4 | 16
5 | 6
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 41 | 9
2 | 32 | 7
3 | 25 | 9
4 | 16 | 10
5 | 6 | 0
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 41 | 9
2 | 32 | 7
3 | 25 | 9
4 | 16 | 10
5 | 6 | 0